## KNM
Prepared by: | Deepa
Report Date | 07.12.22
Site | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178842 | 20.10.22 | kitchen cabinets | follow up to procurement team
178851 | 29.11.22 | SS Hinges | Po issue94793
178852 | 29.11.22 | Araldite | Po issue 94791
178853 | 29.11.22 | Main door lights | Po issue 94789
List of requisitions Where PO/WO is prepared and items have not received at site
178477 | 31.03.22 | Toughened Glass | Delivered
178744 | 05.09.22 | Smile play | Next weak delivery
178764 | 20.09.22 | Ms Grill | Next weak delivery
178787 | 07.10.22 | Tan brown Granite | Next weak delivery
178798 | 18.10.22 | Ms Grill | Next weak delivery
178813 | 31.10.22 | Steel Railing | Next weak delivery
178820 | 05.11.22 | Tan brown Granite | Delivered
178834 | 17.11.22 | Ms Grill | Next weak delivery
178843 | 24.11.22 | Square manhole | Next weak delivery
178845 | 26.11.22 | Copper wires | Next weak delivery
178849 | 26.11.22 | Cp wall mixture | Next weak delivery