## KNM
Prepared by: | Deepa
Report Date | 07.12 .22
Site | GHT
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142284 | 17.10.22 | Fire rated Door | follow up to procurement team
142294 | 20.10.22 | Modular kitchen work order | follow up to procurement team
142376 | 19.11.22 | Fire rated doule leaf door with glass | follow up to procurement team
142409 | 01.12.22 | Cp Plumbing material | po issue 94598
142412 | 01.12.22 | Hammer drill bit | po issue 94658
List of requisitions Where PO/WO is prepared and items have not received at site
142218 | 28.09.22 | Steel Ms grill | Under Fabrication
142235 | 04.10.22 | upvc doors windows | delivered
142238 | 04.10.22 | Glass balcony railong | Delivered
142260 | 09.10.22 | Nitco bilblios tiles | Next weak delivery
142272 | 10.10.22 | Vitrifies tagus tile | pick up from Gmr
142300 | 25.10.222 | Panel doors | pick up from Ssllp
142314 | 31.10.22 | blacowhiten & black berry | pick up from Gmr
142315 | 31.10.22 | luna wall tiles | pick up from Gmr
142331 | 03.11.22 | CC hume pipes | Delivered
142338 | 04.11.22 | Panel doors | Next weak delivery
142349 | 08.11.22 | Coffee powder | Next weak delivery
142357 | 12.11.22 | Panel doors | Next weak delivery
142358 | 12.11.22 | Ms grill | Next weak delivery
142370 | 16.11.22 | Water proofing cement | Next weak delivery
142381 | 21.11.22 | Electrical wires | Delivered
142389 | 22.11.22 | Utility tiles | pick up from Gmr
142390 | 23.11.22 | Bathroom tiles | pick up from Gmr
142392 | 23.11.22 | Bathroom tiles | pick up from Gmr
142398 | 26.11.22 | Electrical wires | Delivered
142401 | 26.11.22 | Panel doors | pick up from Ssllp