## Vista
Prepared by: | Vanajakshi
Report Date | 08.12.2022
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
|  | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
95237 | 4.44.2022 | MS grill | Under fabrication
95239 | 5.11.2022 | Doors and hardware | next week delivery
95240 | 7.11.2022 | Maharaja beige | delivered
95242 | 9.11.2022 | CPVC-FABT | next week delivery
95245 | 12.11.2022 | MS grill | Under fabrication
95251 | 19.11.2022 | Pad locks | Supplier Arranging the material
95253 | 23.11.2022 | Plain bend 100mm&single Y 75mm | next week delivery
95261 | 29.11.2022 | MS grills | Under fabrication
95264 | 30.11.2022 | Plumbing CPVC pipe | next week delivery
95266 | 30.11.2022 | Tiles | Awaiting for arranging the material
95267 | 2.12.2022 | Tiles | Awaiting for arranging the material