## KNM
Prepared by: | Deepa
Report Date | 14.12.22
Site | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178842 | 22.11.22 | kitchen cabinets | Po issue -94434
178865 | 09.12.22 | sign boards | promotions to follow up
178861 | 05.12.22 | Lifts | Estimation send to MD'S approval
178862 | 07.12.22 | Ups | Po issue -94932
List of requisitions Where PO/WO is prepared and items have not received at site
178744 | 05.09.22 | Smile play | Next weak delivery
178764 | 20.09.22 | Ms Grill | Next weak delivery
178787 | 07.10.22 | Tan brown Granite | Next weak delivery
178798 | 18.10.22 | Ms Grill | Next weak delivery
178813 | 31.10.22 | Steel Railing | Next weak delivery
178834 | 17.11.22 | Ms Grill | Next weak delivery
178843 | 24.11.22 | Square manhole | Next weak delivery
178845 | 26.11.22 | Copper wires | Delivered
178849 | 26.11.22 | Cp wall mixture | Delivered
178851 | 29.11.22 | SS hinges | Delivered
178852 | 29.11.22 | Araldite | Delivered
178853 | 29.11.22 | Main door lights | Delivered
178858 | 03.12.22 | Hindware clara neo | Next weak delivery
178860 | 05.12.22 | Ac220v cable 9sensor | Next weak delivery
178863 | 09.12.22 | Tan brown Granite | Next weak delivery
178864 | 09.12.22 | A4 paper bunles | Delivered