## NE
Prepared by: | K Mounika
Report Date | 14.12.2022
Site | Nilgiri Estates
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
175543 | 19.10.2022 | Tiles | next week delivery
175547 | 04.11.2022 | CP sanitary | Pick up from SSLLP
175548 | 04.11.2022 | CP sanitary | Pick up from SSLLP
175556 | 30.11.2022 | CP sanitary | Pick up from SSLLP
175558 | 03.12.2022 | Grass | Next week delivery