## Sheet1
Prepared by: | Venkateshwarlu.P
Report Date | 2022-12-21
Site | GMR
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
208489 | 15.12.2022 | Electrical Wires | Estimate Send to MD Sir
208482 | 14.12.22 | Notice Board | Po To be issue
208481 | 14.12.22 | SD Card | Cash Purchase by raghu
208480 | 14.12.22 | Chambal Water meter | Po To be issue
208478 | 14.12.22 | Smart Phone | Po To be issue
208477 | 13.12.22 | Electrical Wires | Estimate Send to MD Sir
208462 | 10.12.22 | Cpvc Material | Po To be issue
208458 | 09.12.22 | Bituminous damber | Cash Purchase by raghu
208446 | 08.12.22 | Pannal Doors & hardware | PO to Done
208444 | 08.12.22 | Pannal Doors & hardware | PO to Done
208439 | 08.12.22 | Pannal Doors & hardware | PO to Done
208431 | 6.12.22 | Plumbing And general | PO to Done
208430 | 6.12.22 | Electrical Wires | PO to Done
208424 | 03.12.22 | Asbestos Cement Sheets | Po To be issue
208420 | 03.12.22 | Welding Rods | PO to Done
208411 | 02.12.22 | Pvc Drum | PO to Done
208379 | 28.11.22 | Toughned Glass | Po To be issue
208337 | 23.11.22 | Octagonal GI Plole | Estimate Send to MD Sir
208311 | 19.11.22 | Fire Safety Doors | Procurement Finalised
208312 | 19.11.22 | Fire Safety Doors | Procurement Finalised
208310 | 18.11.22 | Fire Safety Doors | Procurement Finalised
208309 | 18.11.22 | Fire Safety Doors | Procurement Finalised
208179 | 27.10.22 | Electrical Tool box | Material Delivered
208107 | 22.10.22 | MS L-Angle | Requisition Closed
208006 | 8.10.22 | Foarm Board | Requisition Closed
193994 | 3.10.22 | Breath Analyzer | Requisition Closed
193892 | 21.09.22 | Tools Brush | Requisition Closed
List of requisitions Where PO/WO is prepared and items have not received at site
Req.No | Req.Date | Item Description | Details of discussion with supplier
208475 | 13.12.22 | Electrical Material | Part Material Deliverd On Tommarow
208473 | 13.12.22 | Electrical Wires | Part Material Deliverd On Tommarow
208471 | 12.12.22 | Luppum bags | Material Delivered
208472 | 12.12.22 | Gate material Rubber Gasket | Material Delivered
208465 | 10.12.22 | Plumbing Material | Material Delivered
208464 | 10.12.22 | Flush Doors and Hardeware | Part ready for Lifting
208461 | 10.12.22 | Cpvc material | Part ready for Lifting
208454 | 09.12.22 | Cpvc FABT | Material Delivered by Tommarow
208446 | 08.12.22 | Pannal Doors & Hardeware | Material received to SSLLP By Saterday
208444 | 08.12.22 | Pannal Doors & Hardeware | Material received to SSLLP By Saterday
208439 | 08.12.22 | Pannal Doors & Hardeware | Material received to SSLLP By Saterday
208430 | 6.12.22 | Electrical Wires | Part Material Deliverd On Tommarow
208381 | 29.11.22 | MS Grills | Its Send For Powder Coating
208370 | 28.11.22 | Eco Drain Chamber | Material delivered
208253 | 12.11.22 | MS Grills | Its Send For Powder Coating
208252 | 12.11.22 | MS Grills | Its Send For Powder Coating
208245 | 10.11.22 | Crackmate Powder | Raedy for Lifting
208193 | 04.11.22 | Dry garbage and Wet garbagee | No Stock at Supplier its Come On Monday
208189 | 04.11.22 | MS Grills | Its Send For Powder Coating its come on Monday
208188 | 04.11.22 | MS Grills | Its Send For Powder Coating
208380 | 29.11.22 | MS Grills | Its Send For Powder Coating
208358 | 25.11.22 | Cp Material | Cp come on Next week
208285 | 16.11.22 | SS Sink | Its Delivered next Week
208278 | 15.11.22 | Pannal Doors & Hardeware | Material received to SSLLP By Next Week
208156 | 27.10.22 | Cpvc Tank Nipple | Cp come on Next week
208144 | 27.10.22 | General Items | Material Delivered
208061 | 18.10.22 | Pvc Drums | Its Delivered by tommarow
208009 | 8.10.22 | MS Grills | Material delivered
193793 | 30.09.22 | MS Grills | Part delivered
193872 | 16.09.22 | Cement Fiber Board | Part delivered
193799 | 16.09.22 | Cement Fiber Board | Its delivered
193773 | 6.09.22 | MS Grills | Part delivered