## KNM
Prepared by: | Deepa
Report Date | 21.12 .22
Site | GHT
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
142284 | 17.10.22 | Fire rated Door | follow up to procurement team
142294 | 20.10.22 | Modular kitchen work order | follow up to procurement team
142376 | 19.11.22 | Fire rated doule leaf door with glass | follow up to procurement team
142415 | 01.12.22 | work order for utility Grill | follow up to procurement team
142456 | 13.12.22 | flat files | pramotions to follow up
142460 | 14.12.22 | Smart phones | Po to be issue
142461 | 15.12.22 | Electrical wires | po issue 95072
List of requisitions Where PO/WO is prepared and items have not received at site
142218 | 28.09.22 | Steel Ms grill | Under Fabrication
142238 | 04.10.22 | Glass balcony railong | Delivered
142260 | 09.10.22 | Nitco bilblios tiles | Delivered
142272 | 10.10.22 | Vitrifies tagus tile | pick up from Gmr
142314 | 31.10.22 | blacowhiten & black berry | pick up from Gmr
142331 | 03.11.22 | CC hume pipes | Delivered
142357 | 12.11.22 | Panel doors | Delivered
142358 | 12.11.22 | Ms grill | Next weak delivery
142370 | 16.11.22 | Water proofing cement | Delivered
142389 | 22.11.22 | Utility tiles | pick up from Gmr
142390 | 23.11.22 | Bathroom tiles | pick up from Gmr
142392 | 23.11.22 | Bathroom tiles | pick up from Gmr
142393 | 23.11.22 | wall putty bags | Delivered
142401 | 26.11.22 | Panel doors | pick up from Ssllp
142405 | 29.11.22 | Ms Grill | Next weak delivery
142409 | 01.12.22 | plumbing cp material | pick up from Ssllp
142410 | 01.12.22 | plumbing cp material | pick up from Ssllp
142430 | 05.12.22 | steel railing | Next weak delivery
142443 | 07.12.22 | Tan brown granite | Next weak delivery