## KNM
Prepared by: | Deepa
Report Date | 21.12.22
Site | MPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
178865 | 09.12.22 | sign boards | Delivered
178871 | 14.12.22 | Balcony glass | po issue-95048
178872 | 14.12.22 | smart phones | po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
178744 | 05.09.22 | Smile play | pick up from supplier
178764 | 20.09.22 | Ms Grill | delivered
178787 | 07.10.22 | Tan brown Granite | Next weak delivery
178798 | 18.10.22 | Ms Grill | Next weak delivery
178813 | 31.10.22 | Steel Railing | Next weak delivery
178834 | 17.11.22 | Ms Grill | Next weak delivery
178843 | 24.11.22 | Square manhole | Next weak delivery
178842 | 22.11.22 | Kitchen cainet | Next weak delivery
178849 | 26.11.22 | Cp wall mixture | Delivered
178858 | 03.12.22 | Hindware clara neo | Next weak delivery
178861 | 05.12.22 | Lifts no 4-38-21-018 service lift | Next weak delivery
178863 | 09.12.22 | Tan brown Granite | Next weak delivery
178869 | 12.12.22 | False ceiling lights | pick up from ssllp
178873 | 16.12.22 | Grout cement | Delivered
178874 | 16.12.22 | Street light | Delivered