## Vista
Prepared by: | Vanajakshi
Report Date | 22.12.2022
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
95286 | 16.12.2022 | Cement | po no:20221217004
95271 | 7.12.2022 | Granite | po no:20221220004
95283 | 14.12.2022 | Smart phone | Po to be issue
List of requisitions Where PO/WO is prepared and items have not received at site
95237 | 4.44.2022 | MS grill | Under fabrication
95239 | 5.11.2022 | Doors and hardware | next week delivery
95242 | 9.11.2022 | CPVC-FABT | Deliveres
95245 | 12.11.2022 | MS grill | Under fabrication
95251 | 19.11.2022 | Pad locks | Supplier Arranging the material
95253 | 23.11.2022 | Plain bend 100mm&single Y 75mm | next week delivery
95261 | 29.11.2022 | MS grills | Under fabrication
95262 | 29.11.2022 | Acid | next week delivery
95266 | 30.11.2022 | Tiles | Awaiting for Arranging the material
95267 | 2.12.2022 | Tiles | Awaiting for Arranging the material
95269 | 5.12.2022 | Stationary | next week delivery
95270 | 6.12.2022 | Wall putty gypsum | next week delivery
95272 | 7.12.2022 | MS L-patti | Delivered
95273 | 7.12.2022 | Door frame | Delivered
95274 | 7.12.2022 | Electrical | Delivered
95275 | 9.12.2022 | Door frame | next week delivery
95276 | 9.12.2022 | Door frame | next week delivery
95277 | 9.12.2022 | Door frame | next week delivery
95278 | 9.12.2022 | Panel door | next week delivery
95280 | 10.12.2022 | Channel bracket | Dewlivered
95281 | 12.12.2022 | MS Z angles | Under fabrication
95282 | 14.12.2022 | Wall putty gypsum | next week delivery