## Vista
Prepared by: | vanajakshi
Report Date | 29.12.2022
Site | Dr.Nrk Biotech
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186472 | 14.12.2022 | Smart phone | PO NO:95497
List of requisitions Where PO/WO is prepared and items have not received at site
186432 | 22.10.2022 | Couplers | Next week delivery
186465 | 12.12.2022 | Spacers | Delivered
186471 | 15.12.2022 | PVC drums | Local purchase by Raghu