## Vista
Prepared by: | vanajakshi
Report Date | 05.01.2023
Site | Dr.Nrk Biotech
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
186432 | 22.10.2022 | Couplers | Next week delivery
186482 | 27.12.2022 | Binding wire | Next week delivery
186471 | 15.12.2022 | PVC drums | Delivered
186481 | 27.12.2022 | Safety Helemets | Delivered