## Vista
Prepared by: | vanajakshi
Report Date | 13.01.2023
Site | Dr.Nrk Biotech
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186486 | 29.12.2022 | Router | Online purchase
186478 | 23.12.2022 | Fire doors | PO:96100
List of requisitions Where PO/WO is prepared and items have not received at site
186432 | 22.10.2022 | Couplers | Next week delivery
186482 | 27.12.2022 | Binding wire | Next week delivery
186489 | 3.01.2023 | Proportion box | Net week delivery
186472 | 14.12.2022 | Smart phone | Delivered