## KNM
Prepared by: | Deepa
Report Date | 24.01.23
Site | NGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
182328 | 28.11.22 | Router | Online purchase
182346 | 06.12.22 | Air Blower | Local purchase
182405 | 18.01.23 | CPVC material | Po issue -96288
182407 | 18.01.23 | Wooden box | Po issue-96237
List of requisitions Where PO/WO is prepared and items have not received at site
182180 | 09.09.22 | Denver beige | awaiting for arranging the material
182355 | 14.12.22 | Anchor bolt | Next week delivery
182373 | 24.12.22 | Tandoor Stone | Next week delivery
182383 | 30.12.22 | HOB | Next week delivery
182389 | 03.01.23 | Cutting Blades | Next week delivery
182392 | 03.01.23 | Oven Fridge | Next week delivery
182403 | 11.01.23 | CPVC material | Next week delivery
182406 | 18.01.23 | Pvc material | Next week delivery