## Villa 1 to 95
Report - details of posession.
Project Name: |  | Silver Oak Villas LLP | Prepared By: | B.Meenakshi |  |  | Date: | 2023-01-25
Block / Phase: |  | Villa nos 1 to 95.& 8 flats
Villa / Flat No. | No. of bedrooms | Customer name | Sate III QC report date | Stage IV completed? (Yes / No) | Possession letter issued by CR? (Yes / No) | Hanover date mentioned in posession letter. | Actual date of posession given. | MMC due from - month/year | Villa occupied by owner / tenant? | Remarks (If possession not given provide details of pending work. If possession was given after due date provide reasons for delay)
1 | 2 BHK | Mrs. K.Mamatha/ Mr. Balraj | 2019-04-27 | Yes | Yes | 2020-03-14 | 2020-07-25 | 2022-10-01 | Yes | Customers not willing to pay
2 | 2 BHK | Mr.Suresh | 2019-04-29 | Yes | Yes | 2020-06-10 | 2020-07-02 | 2022-08-01 | Yes | incresed amount
3 | 2 BHK | Mr. Muvva Bharathi | 2019-04-30 | Yes | Yes | 2020-03-03 | 2020-08-14 | - | Yes
4 | 3 BHK | E. Prabhakar reddy | 2019-04-27 | Yes | Yes | 2019-09-06 | 2019-09-30 | 2022-12-01 | Yes
5 | 3 BHK | Mr. veenish babu | 2019-04-30 | Yes | Yes | 2020-03-31 | 2020-03-02 | - | Yes
6 | 2 BHK | Mr.P.Anandan | 2019-05-21 | Yes | Yes | 2019-10-05 | 2019-11-10 | 2022-11-01 | Yes
7 | 2 BHK | Mr. Thakur Jitendra | 2019-05-27 | Yes | Yes | 2019-11-30 | 2019-11-15 | - | Yes
8 | 2 BHK | Mr.Adarsh | 2019-05-24 | Yes | Yes | 2019-11-30 | 2019-11-15 | 2022-12-01 | Yes
9 | 2 BHK | Mr. K. Veeresh | 2019-05-24 | Yes | Yes | 2020-08-10 | 2020-08-01 | 2022-11-01 | Yes
10 | 2 BHK | Mr. K. Ravi | 2019-05-04 | Yes | Yes | 2020-05-29 | 2020-06-15 | 2023-01-01 | Yes
11 | 3 BHK | Mrs. Sunitha Choudhary | 2018-11-28 | Yes | Yes | 2020-07-30 | 2020-11-21 | 2023-01-01 | Yes
12 | 2 BHK | Mr. Abhay Sekhar | 2019-06-12 | Yes | Yes | 2020-07-31 | 2020-07-10 | 2022-10-01 | Yes
13 | 2 BHK | Mr. Shaik Sinkindar Meerja | 2019-05-27 | Yes | Yes | 2019-09-10 | 2019-09-30 | 2022-12-01 | Yes
14 | 2 BHK | Mr. Abdul Khader | 2019-06-04 | Yes | Yes | 10-19-19 | 2019-09-30 | 2022-12-01 | Yes
15 | 2 BHK | Mr. Jaganadha Raviteja | 2019-05-28 | Yes | Yes | 2019-12-25 | 2020-06-15 | - | Yes
16 | 2 BHK | Mr. D. Chakrapani Reddy | 2019-05-28 | Yes | Yes | 2020-10-15 | 2020-06-15 | - | Yes
17 | 2 BHK | Mr. Surya Venkateshwara | 2019-10-17 | Yes | Yes | 2020-01-20 | 2020-03-04 | 2023-01-01 | Yes
18 | 2 BHK | Mr. Kanaka Rao | 2020-08-18 | Yes | Yes | 2020-09-10 | 2020-09-29 | 2023-01-01 | Yes
19 | 3 BHK | Mr. Shankar Karteek | 2019-11-05 | Yes | Yes | 2020-02-14 | 2020-03-14 | 2022-10-01 | Yes
20 | 2 BHK | Ch. Ramesh | 2019-11-02 | Yes | Yes | 2020-03-20 | 2020-03-20 | 2022-11-01 | Yes
21 | 4 BHK | Mr.Rama Krishna | 2019-11-18 | Yes | Yes | 2019-11-20 | 2019-11-20 | - | Yes
22 | 2 BHK | Col. B.V.Naidu/Mr.Varun Naidu | 2019-09-18 | Yes | Yes | 2020-06-15 | 2020-08-21 | 2022-12-01 | Yes
23 | 2 BHK | Mr.Praveen | 2019-09-06 | Yes | Yes | 2019-09-10 | 2019-10-10 | 2023-01-01 | Yes
24 | 4 BHK | Mrs.Sujatha/Mr. Shanker | 2019-09-11 | Yes | Yes | 2020-03-31 | 2020-07-30 | 2022-11-01 | Yes
25 | 2 BHK | Mr.Anand Sharma | 2019-06-25 | Yes | Yes | 2020-03-20 | 2020-06-06 | 2022-11-01 | Yes
26 | 2 BHK | Mr. Bhaskar Reddy | 2019-06-26 | Yes | Yes | 2020-02-29 | 2020-03-18 | - | Yes
27 | 2 BHK | Mr. T. Ramakrishna | 2019-07-02 | Yes | Yes | 2019-10-01 | 2019-10-20 | 2022-12-01 | Yes
28 | 2 BHK | Mr. Sankati Santhaiah | 2020-01-13 | Yes | Yes | 2020-02-29 | 2020-03-13 | 2022-12-01 | Yes
29 | 3BHK | Srinivas Argatla | 2021-10-09 | Yes | - | - | - |  | - | Possession letter not recived
30 | 3BHK | Raj Kumar | - | - | - | - | - |  | - | -
31 | 3BHK | vamshi Raj lakshmi rajesh | 2022-08-10 | Yes | Yes | 2022-12-05 | 2022-12-05 | - | No | -
32 | 3BHK | Srikanth Vittal | - | - | - | - | - |  | - | -
33 | 2 BHK | Mr. Y. Maheswara | 2020-08-01 | Yes | Yes | 2020-11-10 | 2020-10-29 | 2023-01-01 | Yes
34 | 2 BHK | Mr. Ravi Kanti | 2020-10-16 | Yes | Yes | 2021-01-30 | 2021-01-23 | 2022-10-01 | Yes
35 | 3 BHK | Mr.S.T.Venkateshwara | 2020-07-14 | Yes | Yes | 2020-11-30 | 2020-12-12 | 2022-10-01 | Yes
36 | 2 BHK | Mr. Satish Kuamr | 2020-03-04 | Yes | Yes | 2020-07-10 | 2020-06-19 | 2023-01-01 | Yes
37 | 2 BHK | Mr. Y. Sudheer | 2020-07-16 | Yes | Yes | 2020-10-15 | 2020-09-26 | - | Yes
38 | 4 BHK | Mrs. Uddagiri Thanooja | 2020-11-09 | Yes | Yes | 2021-03-10 | 2021-03-15 | 2022-12-01 | Yes
39 | 3 BHK | Mrs. Manogna | 2020-11-05 | Yes | Yes | 2020-12-15 | 2020-12-28 | 2022-11-01 | Yes
40 | 2 BHK | Mrs. Mallika/ Mureleshwar Rao | 2020-05-15 | Yes | Yes | 2020-07-15 | 2020-07-04 | 2022-12-01 | Yes
41 | 3 BHK | Mrs. lavanya | 2020-01-17 | Yes | Yes | 2020-01-22 | 2020-02-15 | 2022-10-01 | Yes
42 | 3 BHK | Mr. Lakshmi Prasad | 2020-07-18 | Yes | Yes | 2020-08-05 | 2020-07-23 | 2022-12-01 | Yes
43 | 2 BHK | Mr. Shaik Abdul Raheem | 2020-07-02 | Yes | Yes | 2020-10-10 | 2020-09-25 | 2022-11-01 | Yes
44 | 4 BHK | Mr. G. Sandeep | 2020-09-17 | Yes | Yes | 2021-09-25 | 2021-09-26 | 2023-01-01 | Yes
45 | 2 BHK | Mr. Sadaiah | 2020-09-02 | Yes | Yes | 2021-01-20 | 2021-07-28 | 2022-11-01 | Yes
46 | 2 BHK | Mr. Balakrishna | 2020-02-20 | Yes | Yes | 2021-01-20 | 2021-02-12 | 2023-01-01 | Yes
47 | 4 BHK | Mr. Pandu | 2020-06-02 | Yes | Yes | 2021-02-18 | 2021-02-06 | 2022-05-01 | Yes
48 | 3 BHK | Mr. K. Srinivas/ Mrs.Sri valli | 2020-06-19 | Yes | Yes | 2020-08-24 | 2020-11-16 | 2022-10-01 | Yes
49 | 3 BHK | Mr. P.G. Prakash Rao | 2020-06-25 | Yes | Yes | 2020-10-15 | 2021-01-07 | 2023-01-01 | Yes
50 | 2 BHK | Mr. Sumit | 2020-03-19 | Yes | Yes | 2020-07-15 | 2020-07-20 | 2023-01-01 | Yes
51 | 2 BHK | Mr. Praveen Kumar | 2020-07-04 | Yes | Yes | 2020-12-11 | 2020-12-11 | 2022-11-01 | Yes
52 | 2 BHK | Mrs. Sreevalli | 2020-07-06 | Yes | Yes | 2021-01-20 | 2021-01-06 | - | Yes
53 | 2 BHK | Mr. K.G. Venkaiah | 2020-07-31 | Yes | Yes | 2021-04-25 | 2021-08-20 | 2022-10-01 | Yes
54 | 3 BHK | Mr. Vishwanathan | 2020-08-25 | Yes | Yes | 2021-06-24 | 2021-06-24 | 2022-12-01 | Yes
55 | 3 BHK | Mr. Maheshwaran | 2020-08-25 | Yes | Yes | 2021-02-18 | 2021-06-24 | 2022-01-01 | Yes
56 | 3 BHK | Mr. Tangirala | 2020-08-25 | Yes | Yes | 2021-01-15 | 2021-02-05 | 2022-12-01 | Yes
57 | 3 BHK | Mr. Chandra Sekhar | 2020-08-18 | Yes | Yes | 2021-01-20 | 2021-04-23 | 2022-11-01 | Yes
58 | 2 BHK | Mrs. Anuradha | 2020-10-31 | Yes | Yes | 2021-02-10 | 2021-02-06 | 2022-12-01 | Yes
59 | 3 BHK | Mr. Kiran Kumar | 2020-08-18 | Yes | Yes | 2021-03-10 | 2021-01-09 | 2022-11-01 | Yes
60 | 3 BHK | Mr. Satyanarayana | 2021-02-23 | Yes | Yes | 2021-11-15 | 2021-11-22 | 2023-01-01 | Yes
61 | 3 BHK | Mrs. Buddha Ruthmani | 2020-11-09 | Yes | Yes | 2021-03-15 | 2021-03-24 | - | Yes
62 | 2 BHK | Mr. Suresh Kumar | 2020-11-26 | Yes | Yes | 2021-03-05 | 2021-02-27 | 2022-11-01 | Yes
63 | 2 BHK | Mr. T.V.L.N.Pavan Phani | 2020-09-02 | Yes | Yes | 2020-11-25 | 2020-12-14 | 2022-11-01 | Yes
64 | 2 BHK | Mr. V. Raghupathi Reddy | 2020-08-01 | Yes | Yes | 2020-09-23 | 2020-09-23 | 2022-11-01 | Yes
65 | 2 BHK | Mr. M. Nagaraju | 2020-12-09 | Yes | Yes | 2021-03-05 | 2021-03-05 | 2022-10-01 | Yes
66 | 2 BHK | Mr. Venu Madhav | 2020-12-03 | Yes | Yes | 2021-07-15 | 2021-10-25 | 2022-11-01 | Yes
67 | 3 BHK | Mrs. Gayathri | 2020-06-01 | Yes | Yes | 2020-10-15 | 2020-11-05 | 2022-12-01 | Yes
68 | 3 BHK | Mr. Sarkar Amit | 2021-02-23 | Yes | Yes | 2021-07-15 | 2021-09-17 | 2022-12-01 | Yes
69 | 2 BHK | Mr. Aditya Singh Manral | 2021-01-13 | Yes | Yes | 2021-08-31 | 2022-01-05 | 2021-11-01 | Yes
70 | 3 BHK | Mrs.V.Pavithra Bai/Mr.Kiran kumar | 2021-01-04 | Yes | Yes | 2021-06-24 | 2021-06-24 | 2022-11-01 | Yes
71 | 2 BHK | Mr. U.T.Raju | 2020-09-05 | Yes | Yes | 2020-09-11 | 2020-09-20 | 2023-01-01 | Yes
72 | 2 BHK | Mr. Shiva Prasad RaviKanti | 2020-12-21 | Yes | Yes | 2021-05-21 | 2021-07-28 | 2022-12-01 | Yes
73 | 4 BHK | Mr. Sri Ramoju Vijaya Sena | 2021-02-15 | Yes | Yes | 2021-05-21 | 2021-09-15 | - | Yes
74 | 3 BHK | Dr. Bathini Ravi | 2020-11-19 | Yes | Yes | 2021-03-31 | 2021-06-04 | 2022-10-01 | Yes
75 | 2 BHK | Mr. Jupudi Chandrakanth | 2020-12-29 | Yes | Yes | 2021-09-15 | 2021-09-15 | 2022-01-01 | Yes
76 | 3 BHK | Mr. Kotha Kishan | 2021-03-15 | Yes | Yes | 2021-09-15 | 2021-10-25 | 2022-12-01 | Yes
77 | 3 BHK | Mr. Nalla Rajesham | 2020-12-03 | Yes | Yes | 2021-03-25 | 2021-04-24 | - | Yes
78 | 2 BHK | Mr. Rajesh Paul | 2020-06-18 | Yes | Yes | 2020-07-31 | 2020-08-12 | 2022-12-01 | Yes
79 | 2 BHK | Mr. MVSR Ravi Kanth | 2021-01-23 | Yes | Yes | 2022-06-25 | 2022-06-25 | 2022-11-01 | No
80 | 3 BHK | Mr. Pattan Yousuf Khan | 2020-10-16 | Yes | Yes | 2020-12-09 | 2020-12-09 | 2022-12-01 | Yes
81 | 3 BHK | Mrs. Jyothi | 2020-11-12 | Yes | Yes | 2021-03-10 | 2021-03-31 | 2022-11-01 | Yes
82 | 3BHk | T.Venkatesh Rao | 2021-10-09 | Yes | Yes | 2021-11-30 | 2021-11-25 | 2022-11-01 | Yes
83 | 2 BHK | Mr. Sita Raman/ Mrs. S. Srivani | 2020-07-31 | Yes | Yes | 31.10.20 | 2021-02-19 | 2022-11-01 | Yes
84 | 2 BHK | Mr. K. Harinath | 2020-07-23 | Yes | Yes | 2020-09-20 | 2020-09-20 | 2022-10-01 | Yes
85 | 3 BHK | Mr. K. Akshay | 2020-11-12 | Yes | Yes | 2021-12-18 | 2021-12-18 | 2022-10-01 | Yes
86 | 2 BHK | Mr. Praveen kumar | 2020-09-11 | Yes | Yes | 2021-06-04 | 2021-06-04 | - | Yes
87 | 2 BHK | Mr. RVLV Prasad Rao | 2020-06-10 | Yes | Yes | 2020-11-10 | 2020-11-10 | 2022-11-01 | Yes
88 | 2 BHK | Mr. Manmohan Raj | 2020-06-09 | Yes | Yes | 31-06-20 | 2020-07-16 | 2022-07-01 | Yes
89 | 2 BHK | Surya Prathap Singh | 2020-11-09 | Yes | Yes | 31-11-20 | 2020-11-30 | - | Yes
90 | 3 BHK | Mr. Prabhavathi Prakash Rao | 2020-12-22 | Yes | Yes | 2022-02-18 | 2022-02-18 | 2022-07-01 | Yes
91 | 2 BHK | Mr. Bhanu Shiva Prasad | 2020-09-12 | Yes | Yes | 2020-10-31 | 2020-11-06 | 2023-01-01 | Yes
92 | 2 BHK | Mrs. Maha Lakshmi | 2020-12-11 | Yes | Yes | 2021-03-31 | 2021-03-23 | 2023-01-01 | Yes
93 | 4 BHK | Kusuma Kumari | 2021-03-18 | - | - | - | - | - | - | Custmore not took posession
94 | 2 BHK | Mr. Raj Mogli | 2020-12-04 | Yes | Yes | 2021-06-12 | 2021-06-12 | 2022-11-01 | Yes
95 | 3 BHK | Mr.Sanjeev Reddy | 2020-10-31 | Yes | Yes | 2021-10-25 | 2021-10-26 | 2022-10-01 | Yes
99-1A | 3 BHK | Model Flat | - | - | - | - | - |  | -
99-1B | 3 BHK | Model Flat | - | - | - | - | - |  | -
99-2A | 3 BHK | Unsold | - | - | - | - | - |  | -
99-2B | 3 BHK | Unsold | - | - | - | - | - |  | -
99-3A | 3 BHK | Vikram Kumar | 2021-04-26 | Yes | Yes | 2021-09-30 | 2021-12-31 | - | Yes
99-3B | 3 BHK | Priyanaka Bandela | 2021-05-30 | Yes | Yes | 2021-12-31 | 2022-01-08 | - | Yes
99-4A | 3 BHK | Mr. K.Kiran Kumar | 2021-04-26 | Yes | Yes | 2021-12-31 | 2022-02-21 | 2022-07-01 | Yes
99-4B | 3 BHK | Vittal babu Rao | 2021-05-30 | Yes | Yes | 2022-05-18 | 2022-05-19 | 2022-12-01 | Yes
Note: | Make separate sheet for each block / phase.