## 101-214
Report - details of posession.
Project Name: |  | Silver Oak Villas LLP part-III | Prepared By: | B.Meenakshi |  |  | Date: |  | 2023-01-25
Block / Phase: |  | Villa nos 101-214
Villa / Flat No. | No. of bedrooms | Customer name | Sate III QC report date | Stage IV completed? (Yes / No) | Possession letter issued by CR? (Yes / No) | Hanover date mentioned in posession letter. | Actual date of posession given. | MMC due from - month/year | Villa occupied by owner / tenant? | Remarks (If possession not given provide details of pending work. If possession was given after due date provide reasons for delay)
101 | 3bhk | Cuddapah sree & Cuddaph Rangamma Rangaswamy | 2022-03-16 | Yes | Yes | 2022-08-10 | 2022-07-25 | - | Yes | Maintainance not yet started
102 | 3bhk | Bellamknda Pavani | 2022-06-09 | - | - | - | - | - | -
103 | 3bhk | Chunduri Thejovthi | 2022-06-09 | - | - | - | - | - | -
104 | 3bhk | K.N.S.S.S.Srinivas & K.Rekha | 2022-07-04 | Yes | Yes | 2022-08-12 | 2022-08-20 | - | Yes | Maintainance not yet started
105 | 3bhk | Gunduru Naresh | 2022-07-04 | - | - | - | - | - | -
106 | 3bhk | G.Subramanian G. Sangeeta | 2022-05-06 | Yes | Yes | 2022-07-30 | 2022-10-30 | - | No | Maintainance not yet started
107 | 3bhk | Deepti Satya Prasad | 2022-05-25 | Yes | Yes | 2022-08-10 | 2022-07-25 |  | Yes | Maintainance not yet started
108 | 3bhk | Pradeep Mashetti | 2022-08-29 | - | - | - | - | - | - | Data not updated In M codex
109 | 3bhk | Tirupati Pavan Kumar & Tirupati Pragathi | 2022-10-29 | yes | yes | 2022-12-20 | - | - | - | Data not updated In M codex
110 | 3bhk | Azghar Hussain Mohammed and Shaik Reshma Praveen | 2022-07-19 | yes | yes | 2022-12-25 | - | - | -
111 | 3bhk | Pasupuleti Narayana | 2022-07-19 | yes | yes | 2022-12-31 | - | - | -
112 | 3bhk | Neti Gopala Krishna Murthy | 2022-06-03 | Yes | Yes | 2022-08-25 | 2022-08-11 |  | Yes | Maintainance not yet started
113 | 3bhk | Sanjeev Reddy | 2022-09-14 | - | - | - | - | - | - | Data not updated In M codex
114 | 3bhk | Bathula Pramada Rani | 2022-04-14 | Yes | Yes | 2022-11-10 | 2022-12-08 | - | No
115 | 3bhk | Savaram Ram Mohana Rao | 2022-08-28 | Yes | Yes | 2022-08-25 | 2022-08-19 | - | Yes | Maintainance not yet started
116 | 3bhk | Iruvanti Ram Aakarsh & Iruvanti Kameswari | 2022-04-14 | Yes | Yes | 2022-08-22 | 2022-08-19 |  | Yes | Maintainance not yet started
117 | 3bhk | Shaik Farooq Abdullah | 2022-07-11 | Yes | Yes | 2022-11-01 | 2022-10-20 | - | Yes | Maintainance not yet started
118 | 3bhk | Theruthomala Shashidar | 2022-07-13 | - | - | - | - | - | -
119 | 3bhk | Ramchandra Murthy VVNS | 2022-08-29 | - | - | - | - | - | - | Data not updated In M codex
120 | 3bhk | Vemula Venkateswar Rao | 2022-09-14 | - | - | - | - | - | - | Data not updated In M codex
121 | 3bhk | Srinivas Dutt | 2022-09-07 | - | Yes | 2022-12-05 | - | - | - | Data not updated In M codex
122 | 3bhk | Sankalp Gabbita | 2022-09-07 | - | - | - | - | - | - | Data not updated In M codex
123 | 3bhk | Sandya Rani Lingamapally | 2022-07-04 | Yes | Yes | 2022-11-30 | - | - | -
124 | 3bhk | Mrs Bhimana Vajhula Hymavathi & B.R.Venkatapathi | 2022-09-02 | - | - | - | - | - | - | Data not updated In M codex
125 | 3bhk | Chandra kala | 2022-06-21 | Yes | Yes | 2022-11-30 | - | - | -
126 | 3bhk | Mannava RamaKrishna | 2022-06-04 | - | Yes | 2022-12-20 | - | - | -
127 | 3bhk | Ms.Anubha Mathew | 2022-06-02 | Yes | Yes | 2022-09-15 | 2022-09-15 | - | Yes | Maintainance not yet started
128 | 3bhk | Anuradha .Kothapalli | 2021-05-05 | Yes | Yes | 2022-08-12 | 2022-08-12 | - | Yes | Maintainance not yet started
129 | 3bhk | Hanumanth Shangrala | 2021-05-05 | Yes | Yes | 2022-07-30 | 2022-08-01 | - | Yes | Maintainance not yet started
130 | 3bhk | Pankaj Kumar Goel Nidhi Goel | 2022-03-12 | Yes | Yes | 2022-08-20 | 2022-08-02 | - | Yes | Maintainance not yet started
131 | 3bhk | Bishwjeet Kumar Baby Singh | 2022-05-10 | Yes | Yes | 2022-07-30 | 2022-07-29 | - | Yes | Maintainance not yet started
132 | 3bhk | Prashant Narayanrao Bawankar / Vaishali Prashant | 2022-05-05 | Yes | Yes | 2022-07-31 | 2022-08-02 | - | Yes | Maintainance not yet started
133 | 3bhk | Sadanand Bhojak | 2022-07-12 | - | - | - | - | - | -
134 | 3bhk | Tangirala Jaya Durga Bhavani | 2022-06-15 | Yes | Yes | 2022-08-25 | 2022-08-30 | - | Yes | Maintainance not yet started
135 | 3bhk | Nasani Narendra | 2022-08-18 | - | - | - | - | - |  | Data not updated In M codex
136 | 3bhk | N/A | - | - | - | - | - | - | -
137 | 3bhk | Uday Kiran Aelagandula | 2022-11-09 | - | - | - | - | - | -
138 | 3bhk | Venkatesh Vaddepally | 2022-11-09 | - | - | - | - | - | -
139 | 3bhk | Vishal Bharath & Mounika | - | - | - | - | - | - | -
140 | 3bhk | Bokka Rajender Reddy | - | - | - | - | - | - | -
141 | 3bhk | Kusuma Mahender Kusuma | - | - | - | - | - | - | -
142 | 3bhk | Shalina Nair | 2022-10-19 | - | - | - | - | - | -
143 | 3bhk | Madhunakar Gottipamula | - | - | - | - | - | - | -
144 | 3bhk | Supriya .Mrs | - | - | - | - | - | - | -
145 | 3bhk | Avinash Navaratna | - | - | - | - | - | - | -
146 | 3bhk | NSVS sai srinivas&anuradha | - | - | - | - | - | - | -
147 | 3bhk | N/A | - | - | - | - | - | - | -
148 | 3bhk | Rajendhar Kodepaka | - | - | - | - | - | - | -
149 | 3bhk | Siri Kelothu | - | - | - | - | - | - | -
150 | 3bhk | Ramesh Babu | - | - | - | - | - | - | -
151 | 3bhk | Hari Kelothu | - | - | - | - | - | - | -
152 | 3bhk | Pradeep .Mr | - | - | - | - | - | - | -
153 | 3bhk | Mamta Tiwari | - | - | - | - | - | - | -
154 | 3bhk | Ravi N | - | - | - | - | - | - | -
155 | 3bhk | Swetha Jakka/Vijay | - | - | - | - | - | - | -
156 | 3bhk | Arun Akella | - | - | - | - | - | - | -
157 | 3bhk | Joharapuram Rafiq | - | - | - | - | - | - | -
158 | 3bhk | B.Chandrakala/Lenin Kumar | 2022-10-20 | - | - | - | - | - | -
159 | 3bhk | Laxman Noonsavath | - | - | - | - | - | - | -
160 | 3bhk | Srinivasa Rao | - | - | - | - | - | - | -
161 | 3bhk | Tapan KV | - | - | - | - | - | - | -
162 | 3bhk | Kodukula Srinivasa Rao / Sudharshan | - | - | - | - | - | - | -
163 | 3bhk | Phani Shankar | - | - | - | - | - | - | -
164 | 3bhk | Naga Sai Aditya | - | - | - | - | - | - | -
165 | 3bhk | Karna S Mehta | - | - | - | - | - | - | -
166 | 3bhk | Sreedhar Subbarao Amere | - | - | - | - | - | - | -
167 | 3bhk | Juny Escolas Dsouza | - | - | - | - | - | - | -
168 | 3bhk | K.Savitri Chatarji | - | - | - | - | - | - | -
169 | 3bhk | K.Shailesh &k.Srikanth | - | - | - | - | - | - | -
170 | 3bhk | Veena Bhat | - | - | - | - | - | - | -
171 | 3bhk | K.Sohith& K.Hymavathi | - | - | - | - | - | - | -
172 | 3bhk | N/A | - | - | - | - | - | - | -
173 | 3bhk | N/A | - | - | - | - | - | - | -
174 | 3bhk | Sunder Rao | - | - | - | - | - | - | -
175 | 3bhk | Koneti Nanaji | - | - | - | - | - | - | -
176 | 3bhk | G Sarada | - | - | - | - | - | - | -
177 | 3bhk | Shashank .K Sabitha | - | - | - | - | - | - | -
178 | 3bhk | saritha thittappillil kirshnan | - | - | - | - | - | - | -
179 | 3bhk | Surya Prasad Rao | - | - | - | - | - | - | -
180 | 3bhk | Rajiv Das | - | - | - | - | - | - | -
181 | 3bhk | Phanindranath .R | - | - | - | - | - | - | -
182 | 3bhk | Sesha Giri | - | - | - | - | - | - | -
183 | 3bhk | Prasad Dasari | - | - | - | - | - | - | -
184 | 3bhk | Prasanna Venkatesh Sridhar | - | - | - | - | - | - | -
185 | 3bhk | Udigiri Charan Kumar | - | - | - | - | - | - | -
186 | 3bhk | N/A | - | - | - | - | - | - | -
187 | 3bhk | N/A | - | - | - | - | - | - | -
188 | 3bhk | N/A | - | - | - | - | - | - | -
189 | 3bhk | N/A | - | - | - | - | - | - | -
190 | 3bhk | N/A | - | - | - | - | - | - | -
191 | 3bhk | N/A | - | - | - | - | - | - | -
192 | 3bhk | N/A | - | - | - | - | - | - | -
193 | 3bhk | N/A | - | - | - | - | - | - | -
194 | 3bhk | N/A | - | - | - | - | - | - | -
195 | 3bhk | N/A | - | - | - | - | - | - | -
196 | 3bhk | N/A | - | - | - | - | - | - | -
197 | 3bhk | N/A | - | - | - | - | - | - | -
198 | 3bhk | N/A | - | - | - | - | - | - | -
199 | 3bhk | N/A | - | - | - | - | - | - | -
200 | 3bhk | N/A | - | - | - | - | - | - | -
201 | 3bhk | N/A | - | - | - | - | - | - | -
202 | 3bhk | N/A | - | - | - | - | - | - | -
203 | 3bhk | N/A | - | - | - | - | - | - | -
204 | 3bhk | N/A | - | - | - | - | - | - | -
205 | 3bhk | N/A | - | - | - | - | - | - | -
206 | 3bhk | N/A | - | - | - | - | - | - | -
207 | 3bhk | N/A | - | - | - | - | - | - | -
208 | 3bhk | Mortagage | - | - | - | - | - | - | -
209 | 3bhk | Mortagage | - | - | - | - | - | - | -
210 | 3bhk | Mortagage | - | - | - | - | - | - | -
211 | 3bhk | Mortagage | - | - | - | - | - | - | -
212 | 3bhk | Mortagage | - | - | - | - | - | - | -
213 | 3bhk | Mortagage | - | - | - | - | - | - | -
214 | 3bhk | N/A | - | - | - | - | - | - | -
Note: | Make separate sheet for each block / phase.
2970