## KNM
Prepared by: | Deepa
Report Date | 22.02.23
Site | NGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
182180 | 09.09.22 | Denver beige | awaiting for arranging the material
182406 | 18.01.23 | pvc material | Next week delivery
182407 | 18.01.23 | Cpvc material | Delivered
182413 | 24.01.23 | Switch | Delivered
182423 | 31.01.23 | GI clamps | Next week delivery
182433 | 15.02.23 | Non return valve | Delivered