## Vista
Prepared by: | vanajakshi
Report Date | 23.02.2023
Site | Dr.Nrk Biotech
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186486 | 29.12.2022 | Router | PO:97235
List of requisitions Where PO/WO is prepared and items have not received at site
186478 | 13.12.2022 | Fire doors | Next week delivery