## KNM
Prepared by: | Deepa
Report Date | 01.03.23
Site | NGH
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
182180 | 09.09.22 | Denver beige | awaiting for arranging the material
182328 | 28.11.22 | Router | Delivered
182423 | 31.01.23 | GI clamps | Next week delivery
182433 | 15.02.23 | Non return valve | Delivered
182434 | 20.02.23 | spacers | Next week delivery
182436 | 25.02.23 | pvc material | Next week delivery