## Sheet2
Modi Realty Miryalguda LLP (22-23)
5-4-187/3 & 4, IInd Floor, Soham Mansion
M G Road, Secunderabad.
CONT- Ashok Constructions A/c
Ledger Account
Plot No:-69 &70,Flat No:-G-7,Sai Pujitha Residency
A S Raju Nagar,Kukatpally,Hyd
1-Apr-22 to 13-Feb-23
Date | Particulars |  | Vch Type | Vch No. | Debit | Credit
2022-04-01 | By | Opening Balance |  |  |  | 6287627.14
2022-04-12 | To | (as per details) | Payment | PAY/10043 | 26600
|  | TDS-2% Contract |  |  |  | 532
|  | BANK- Yes Bank 009763700001888 |  |  |  | 26068
Being online transfer to Ashok Constructions towards truky payment
2022-04-18 | To | (as per details) | Payment | PAY/10080 | 26600
|  | TDS-2% Contract |  |  |  | 532
|  | BANK- Yes Bank 009763700001888 |  |  |  | 26068
Being online transfer to Ashok Constructions towards turnkey contractor
2022-04-25 | To | BANK- Yes Bank 009763700001888 | Payment | PAY/10105 | 26600
Being online trasfer to Ashok constructions towards turkey contractor
2022-04-30 | To | BANK- Yes Bank 009763700001888 | Payment | PAY/10128 | 13300
Being online trasfer to Ashok constructions towards turkey contractor
2022-04-30 | By | (as per details) | Purchase | PUR/10022 |  | 193284
|  | LSRD-Labour Charges 18% |  |  | 65520
|  | LSRD-Allowance for Equipment 18% |  |  | 65520
|  | LSRD-Allowance for Consumables 18% |  |  | 32760
|  | Input CGST |  |  | 14742
|  | Input SGST |  |  | 14742
Being amount credited to Ashok Constructions towards villa no 38 5th stage work 10% completed platering over skirting minor finishing works edge building vide bill no AGH/22-23/1 DT:-04-04-22
2022-04-30 | By | (as per details) | Purchase | PUR/10023 |  | 193284
|  | LSRD-Labour Charges 18% |  |  | 65520
|  | LSRD-Allowance for Equipment 18% |  |  | 65520
|  | LSRD-Allowance for Consumables 18% |  |  | 32760
|  | Input CGST |  |  | 14742
|  | Input SGST |  |  | 14742
Being amount credited to Ashok Constructions towards villa no 39 5th stage work 10% completed platering over skirting minor finishing works edge building vide bill no AGH/22-23/2 DT:-04-04-22
2022-05-11 | To | (as per details) | Payment | PAY/10153 | 300000
|  | TDS-2% Contract |  |  |  | 6000
|  | BANK- Yes Bank 009763700001888 |  |  |  | 294000
Being online trasfer to Ashok constructions towards turkey contractor
2022-06-18 | To | (as per details) | Payment | PAY/10283 | 5125
|  | TDS-2% Contract |  |  |  | 103
|  | BANK- Yes Bank 009763700001888 |  |  |  | 5022
Being online transfer to Ashok Constructions towards turkey contractor
2022-06-27 | To | (as per details) | Payment | PAY/10302 | 5125
|  | TDS-2% Contract |  |  |  | 103
|  | BANK- Yes Bank 009763700001888 |  |  |  | 5022
Being online transfer to Ashok Constructions towards turkey contractor
2022-06-28 | By | (as per details) | Purchase | PUR/10082 |  | 114313
|  | LSRD-Labour Charges 18% |  |  | 38750
|  | LSRD-Allowance for Equipment 18% |  |  | 38750
|  | LSRD-Allowance for Consumables 18% |  |  | 19375
|  | Input CGST |  |  | 8718.75
|  | Input SGST |  |  | 8718.75
|  | OIE-Rounded Off |  |  | 0.5
Being amount credited to Ashok Constructios towards Villa no 44 5th stage work 10% completed plastering over skirting,Minor finishing works edge building ect Vide bill no AGH/22-23/5 DT:-22-06-22
2022-06-28 | By | (as per details) | Purchase | PUR/10083 |  | 207090
|  | LSRD-Labour Charges 18% |  |  | 70200
|  | LSRD-Allowance for Equipment 18% |  |  | 70200
|  | LSRD-Allowance for Consumables 18% |  |  | 35100
|  | Input CGST |  |  | 15795
|  | Input SGST |  |  | 15795
Being amount credited to Ashok Construction towards villa no 70 5th stage work 10% completed plastering over skirting,minor finishing works, edge building etc vide bill no AGH/22-23/4 DT:-10-06-22
2022-06-28 | By | (as per details) | Purchase | PUR/10084 |  | 207090
|  | LSRD-Labour Charges 18% |  |  | 70200
|  | LSRD-Allowance for Equipment 18% |  |  | 70200
|  | LSRD-Allowance for Consumables 18% |  |  | 35100
|  | Input CGST |  |  | 15795
|  | Input SGST |  |  | 15795
Being amount credited to Ashok Construction towards villa no 01 5th stage work 10% completed plastering over skirting,minor finishing works, edge building etc vide bill no AGH/22-23/4 DT:-10-06-22
2022-07-06 | To | (as per details) | Payment | PAY/10326 | 5125
|  | TDS-2% Contract |  |  |  | 103
|  | BANK- Yes Bank 009763700001888 |  |  |  | 5022
Being online transfer to Ashok Constructions towards turkey contractor
2022-07-12 | To | (as per details) | Payment | PAY/10345 | 5125
|  | TDS-2% Contract |  |  |  | 103
|  | BANK- Yes Bank 009763700001888 |  |  |  | 5022
Being online transfer to Ashok Constructions towards turkey contractor
2022-07-18 | To | (as per details) | Payment | PAY/10368 | 5125
|  | TDS-2% Contract |  |  |  | 103
|  | BANK- Yes Bank 009763700001888 |  |  |  | 5022
Being online transfer to Ashok Constructions towards turkey contractor
2022-07-23 | To | (as per details) | Payment | PAY/10377 | 5125
|  | TDS-2% Contract |  |  |  | 103
|  | BANK- Yes Bank 009763700001888 |  |  |  | 5022
Being online transfer to Ashok Constructions towards turkey contractor
2022-07-30 | To | (as per details) | Payment | PAY/10404 | 5125
|  | TDS-2% Contract |  |  |  | 103
|  | BANK- Yes Bank 009763700001888 |  |  |  | 5022
Being online transfer to Ashok Constructions towards turkey contractor
2022-09-19 | To | (as per details) | Payment | PAY/10494 | 300000
|  | TDS-2% Contract |  |  |  | 6000
|  | BANK- Yes Bank 009763700001888 |  |  |  | 294000
being amount transfered
2023-01-05 | By | (as per details) | Purchase | PUR/10374 |  | 207090
|  | LSRD-Labour Charges 18% |  |  | 175500
|  | Input CGST |  |  | 15795
|  | Input SGST |  |  | 15795
Being amount credited to Ashok Construction towards villa no 82 final stage work completed plastering over skirting,minor finishing works, edge building etc vide bill no AGH/22-23/20 dt.11.12.22
2023-01-05 | By | (as per details) | Purchase | PUR/10375 |  | 207090
|  | LSRD-Labour Charges 18% |  |  | 175500
|  | Input CGST |  |  | 15795
|  | Input SGST |  |  | 15795
Being amount credited to Ashok Construction towards villa no.81 final stage work completed plastering over skirting,minor finishing works, edge building etc vide bill no AGH/22-23/19 dt.11.12.22
2023-01-05 | By | (as per details) | Purchase | PUR/10376 |  | 207090
|  | LSRD-Labour Charges 18% |  |  | 175500
|  | Input CGST |  |  | 15795
|  | Input SGST |  |  | 15795
Being amount credited to Ashok Construction towards villa no.69 final stage work completed plastering over skirting,minor finishing works, edge building etc vide bill no AGH/22-23/17 dt.11.12.22
2023-01-05 | By | (as per details) | Purchase | PUR/10377 |  | 207090
|  | LSRD-Labour Charges 18% |  |  | 175500
|  | Input CGST |  |  | 15795
|  | Input SGST |  |  | 15795
Being amount credited to Ashok Construction towards villa no.68 final stage work completed plastering over skirting,minor finishing works, edge building etc vide bill no AGH/22-23/16 dt.11.12.22
2023-01-05 | By | (as per details) | Purchase | PUR/10378 |  | 207090
|  | LSRD-Labour Charges 18% |  |  | 175500
|  | Input CGST |  |  | 15795
|  | Input SGST |  |  | 15795
Being amount credited to Ashok Construction towards villa no.26 final stage work completed plastering over skirting,minor finishing works, edge building etc vide bill no AGH/22-23/13 dt.11.12.22
2023-01-05 | By | (as per details) | Purchase | PUR/10379 |  | 207090
|  | LSRD-Labour Charges 18% |  |  | 175500
|  | Input CGST |  |  | 15795
|  | Input SGST |  |  | 15795
Being amount credited to Ashok Construction towards villa no.18 final stage work completed plastering over skirting,minor finishing works, edge building etc vide bill no AGH/22-23/11 dt.11.12.22
2023-01-09 | To | (as per details) | Payment | PAY/10803 | 1000000
|  | TDS-2% Contract |  |  |  | 20000
|  | BANK- Yes Bank 009763700001888 |  |  |  | 980000
being online trfr to ashok constructions towards as per annex- G payment paid (
|  | 1728975 |  |  |  | 8445228.14
| To | Closing Balance | 6716253.14
|  | 8445228.14 |  |  |  | 8445228.14