## Vista
Prepared by: | vanajakshi
Report Date | 24.03.2023
Site | Dr.Nrk Biotech
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
186571 | 8.03.2023 | Coffee Manchine | searching for a new supplier to make order
List of requisitions Where PO/WO is prepared and items have not received at site
186478 | 13.12.2022 | Fire doors | Delivered
186565 | 2.03.2023 | Sofia grey | Next week delivery