## Vista
Prepared by: | Asha jyothi
Report Date | 23-06-2023 to 09-08-2023
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil
List of requisitions Where PO/WO is prepared and items have not received at site
20230623036 | 2023-06-23 | 2,3 | MS Z-Angle | Will be delivered in 3-4 days
20230630050 | 2023-06-30 | 1 | Breath analyser | Delivery after 2-3 days
20230704001 | 2023-07-04 | 1 | Sports | Next week delivery
20230721015 | 2023-07-21 | 3 | Electrical-Round covers | Delivery after doing bill
20230728003 | 2023-07-28 | 1 to 3 | Windows-UPVC | Delivery on Friday
20230728004 | 2023-07-28 | 1 to 3 | Windows-UPVC | Delivery on Friday
20230728005 | 2023-07-28 | 1 to 3 | Windows-UPVC | Delivery on Friday
20230720016 | 2023-07-20 | 3 | General item-Carrom board cover | Delivery after 2-3 days
20230807026 | 2023-08-07 | 1 | Furniture & Fixtures | Next week delivery
20230807037 | 2023-08-07 | 1,2,3,4 | General item -Safety shoe | Delivered
20230805008 | 2023-08-05 | 1 | Hardware | Will be delivered in 2-3 days
20230809040 | 2023-08-09 | 1 to 15 | Plumbing | Will be delivered in 2-3 days
20230809055 | 2023-08-09 | 1 to 9 | Hardware | Delivered
20230809045 | 2023-08-09 | 1 to 13 | Plumbing | Delivered