## Vista
Prepared by: | S.Jaysudha
Report Date | 2023-08-17
Site | Dr. NRK
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Delivered
20230809037 | 2023-08-09 | Vinle flooring | Po.Done-Deliver by Wednesday
20230809041 | 2023-08-09 | SD Card | Cancelled by Sunil Sir
List of requisitions Where PO/WO is prepared and items have not received at site
20230513022 | 13.05.23 | Nitobond bonding agent
20230620027 | 2023-07-20 | Fire rated doors | Under Production