## NE
Prepared by: | K Mounika
Report Date | 24-08-2023
Site | SOV-III
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
20230605034 | 05.06.2023 | CPVC Fittings | Next week delivery
20230619039 | 19.06.2023 | Panel Door | Next week delivery
20230626034 | 26.06.2023 | HDPE Overhead tank | Collect from SSLLP
20230624010 | 24.06.2023 | CPVC Fittings | Material recieved
20230628053 | 28.06.2023 | Solid Blocks | Follow up with supplier
20230719021 | 19.07.2023 | Electrical (Metal box 6 module) | Next week delivery
2023071025 | 19.07.2023 | Electrical (Metal box 6 module) | Next week delivery
20230725014 | 25.07.2023 | Cylindrical locksand SShinges | Part recieved balance next week delivery
20230725010 | 25.07.2023 | Panel Doors | Material recieved
20230725050 | 25.07.2023 | Electrical copper wires | Collect from SSLLP
| 31.07.2023 | PVC pipes and fittings | Material recieved
| 1.08.2023 | Cutting blades | Material recieved
20230801023 | 1.08.2023 | SS Screws | Part recieved balance next week delivery
20230802001 | 02.08.2023 | Test apparatus slump cone | Follow up with supplier
20230804023 | 04.08.2023 | False ceiling | Work under progress
20230807021 | 07.08.2023 | Wall hung EWC ,Angle cock,Sink cock,wallmixture | Material recieved
20230809002 | 09.08.2023 | janatha paste, tile grout, | Next week delivery
20230809003 | 09.08.2023 | concumbles,cleaning material | Next week delivery
20230811015 | 11.08.2023 | Tan Brown granite | Part recieved balance next week delivery
20230811039 | 11.08.2023 | PVC pipes | Next week delivery
20230814008 | 14.08.2023 | Z Angles | Next week delivery