## Vista
Prepared by: | Asha jyothi
Report Date | 23-06-2023 to 19-08-2023
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil
List of requisitions Where PO/WO is prepared and items have not received at site
20230623036 | 2023-06-23 | 2,3 | MS Z-Angle | Nextweek delivery
20230630050 | 2023-06-30 | 1 | Breath analyser | Next week purchase
20230704001 | 2023-07-04 | 1 | Sports | Supplier arranging material
20230721015 | 2023-07-21 | 3 | Electrical-Round covers | Delivered by tomorrow
20230720016 | 2023-07-20 | 3 | General item-Carrom board cover | Next week purchase
20230807026 | 2023-08-07 | 1 | Furniture & Fixtures | Under fabrication
20230809040 | 2023-08-09 | 1 to 15 | Plumbing | Collect from ssllp in 2-3 days
20230816057 | 2023-08-16 | 1 to 5 | Plumbing | Collect from ssllp in 2-3 days
20230818026 | 2023-08-18 | 1 | Consumables | Nextweek delivery
20230819059 | 2023-08-19 | 1 to 13 | Tiles | Material is ready collect from ssllp