## NE
Prepared by: | jaysudha
Report Date | 24.08.2023
Site | DR.NRK
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
20230809037 | 09.08.2023 | Vinyl flooring | Delivery by friday
20230814020 | 14.08.2023 | manhole covers | Delivery by monday
20230620027 | 20.06.2023 | fire rated doors | Under process