## Vista
Prepared by: | Asha jyothi
Report Date | 23-06-2023 to 25-08-2023
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil
List of requisitions Where PO/WO is prepared and items have not received at site
20230623036 | 2023-06-23 | 2,3 | MS Z-Angle | Nextweek delivery
20230630050 | 2023-06-30 | 1 | Breath analyser | Online purchae
20230704001 | 2023-07-04 | 1 | Sports | Supplier arranging material
20230721015 | 2023-07-21 | 3 | Electrical-Round covers | Will delivered by this week
20230720016 | 2023-07-20 | 3 | General item-Carrom board cover | Online purchase
20230807026 | 2023-08-07 | 1 | Furniture & Fixtures | Nextweek delivery
20230818026 | 2023-08-18 | 1 | Consumables | PO Closed,raise new requisition
20230821051 | 2023-08-21 | 1 | Tools-cutting blade | Received
20230820001 | 2023-08-20 | 1 | General item-Agro net | Received
20230819059 | 2023-08-19 | 1 to 13 | Tiles | Collect material on tomorrow
20230818025 | 2023-08-18 | 4,5,7,8 | Consumables | Received
20230819058 | 2023-08-19 | 1,2,3 | Electrical-MCB | Received
20230820002 | 2023-08-20 | 1 | Electrical-LED Bulb | Received
20230823023 | 2023-08-23 | 6,11 | Electrical | Received
20230824014 | 2023-08-24 | 1 | Stationary | Received
20230823025 | 2023-08-23 | 6,7 | Electrical | Received
20230823021 | 2023-08-23 | 1 | Tiles | Received
20230825004 | 2023-08-25 | 1 | Plumbing-CPVC FTA | Received