## Vista
Prepared by: | Asha jyothi
Report Date | 23-06-2023 to 31-08-2023
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil
List of requisitions Where PO/WO is prepared and items have not received at site
20230623036 | 2023-06-23 | 2,3 | MS Z-Angle | Powder coating pending
20230630050 | 2023-06-30 | 1 | Breath analyser | Online purchae
20230704001 | 2023-07-04 | 1 | Sports | Supplier arranging material
20230720016 | 2023-07-20 | 3 | General item-Carrom board cover | Online purchase
20230807026 | 2023-08-07 | 1 | Furniture & Fixtures | Under fabrication
20230818026 | 2023-08-18 | 1 | Consumables | PO Closed,raise new requisition
20230819059 | 2023-08-19 | 1 to 13 | Tiles | Collect material from ssllp
20230823021 | 2023-08-23 | 1 | Tiles | Collect material from ssllp
20230831002 | 2023-08-31 | 1 to 8 | Plumbing | Collect material from ssllp
20230831011 | 2023-08-31 | 1,3,4,5,6 | Plumbing | Deliverd within this week
20230831012 | 2023-08-31 | 2 | Hardware | Collect material from ssllp