## NE
Prepared by: | K Mounika
Report Date | 06.09.2023
Site | SOV-III
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
20230605034 | 05.06.2023 | CPVC Fittings | Next week delivery
20230619039 | 19.06.2023 | Panel Door | Next week delivery
20230725014 | 25.07.2023 | Cylindrical locksand SShinges | Part recieved balance next week delivery
20230725010 | 25.07.2023 | Panel Doors | Material recieved
20230802001 | 02.08.2023 | Test apparatus slump cone | Follow up with supplier
20230811015 | 11.08.2023 | Tan Brown granite | Part recieved balance next week delivery
20230816018 | 16.08.2023 | wall putty cement | Next week delivery
20230819013 | 19.08.2023 | Stationary | Collect from SSLLP
20230821017 | 21.08.2023 | CP extention nipple ,waste coupling | Collect from SSLLP
20230821018 | 21.08.2023 | wash basin waste coupling | Follow up with supplier
20230821018 | 21.08.2023 | wash basin waste coupling | Follow up with supplier
20230828048 | 28.08.2023 | Electrical Conducting bends | Collect from SSLLP
20230828054 | 28.08.2023 | SS Screws | Follow up with supplier
20230719021 | 19.07.2023 | Metal box 6 way | Material recieved
20230719025 | 19.07.2023 | Metal box 6 way | Material recieved
20230725050 | 25.07.2023 | Electrical copper wires | Material recieved
20230801023 | 01.08.2023 | SS Screws | Material recieved
20230809002 | 09.08.2023 | Janatha paste ,Tile grout | Material recieved
20230811039 | 11.08.2023 | PVC Pipe | Material recieved
20230817004 | 17.08.2023 | CPVC Elbow ,Door Bend | Material recieved
20230818035 | 18.08.2023 | Electrical Switches | Material recieved
20230818036 | 18.08.2023 | Metal box 6 way | Material recieved
20230823003 | 23.08.2023 | Tiles | Material recieved
20230823005 | 23.08.2023 | Gunny bags | Material recieved
20230828046 | 28.08.2023 | Tiles | Material recieved
20230828050 | 28.08.2023 | Eco drain pipe,Riser & chamber | Material recieved
20230828051 | 28.08.2023 | Eco drain pipe,Riser | Material recieved