## NE
Prepared by: | K Mounika
Report Date | 2023-06-09
Site | MHPL
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
20230328042 | 28.03.2023 | Solid bricks | Follow up with supplier
20230516017 | 16.05.2023 | Hollow bricks | Follow up with supplier
|  | Portble toilets | Material recieved DC not recieved
20230703036 | 03.07.2023 | CPVC Fittings | Next week delivery
20230711036 | 11.07.2023 | Paints | Next week delivery
20230712006 | 12.07.2023 | Precast Compound wall | Follow up with supplier
20230814029 | 14.08.2023 | UPS,Micro SD Card | Follow up with supplier
20230829007 | 29.08.2023 | Tandoor Rough stone | Follow up with supplier