## Sheet1
Prepared by: | Venkateshwarlu.P
Report Date | 08.09.2023
Site | GMR
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks
20230808055 | 2023-08-08 | Fire safety Alarm | Po done
20230821010 | 2023-08-21 | Expansio Mortar | Req.Cancelled by site
20230829034 | 2023-08-29 | Spilt AC 2 tone 3 nos | Po done
20230829035 | 2023-08-29 | Door frame with thershold | Po done
20230830052 | 2023-08-30 | Cable round flexible 3 core | Po done
List of requisitions Where PO/WO is prepared and items have not received at site
Req.N+A+A15:D45 | Req.Date | Item Description | Details of discussion with supplier
208064 | 2022-10-15 | Electrical power supply(E,F,club house) | Work under progress
20230506004 | 2023-05-06 | Tan brown granite | Material ready for lifting at SSLLP
20230602037 | 2023-06-02 | Diesel generator | Under progress
20230603015 | 2023-06-03 | Double leaf and singke leaf fire doors | Supplier not Responding to calls
20230608026 | 2023-06-08 | Panel doors 5 nos balance | No stock at SSLLP its received by next week
20230619014 | 2023-06-19 | Lift C block | Under Process
20230619012 | 2023-06-19 | Lift A block | Under Process
20230619013 | 2023-06-19 | Lift B block | Under Process
20230619015 | 2023-06-19 | Lift D block | Under Process
20230619016 | 2023-06-19 | Lift F block | Under Process
20230619017 | 2023-06-19 | Lift G block | Under Process
20230626032 | 2023-06-26 | Fire rated door double leaf | Under Process
20230701002 | 2023-07-01 | Toughned glass | Work under progresss
20230701003 | 2023-07-01 | Toughned glass | Work under progress
20230718019 | 2023-07-18 | Single leaf fire rated door | Under Process
20230731016 | 2023-07-31 | Hydrant valve | Material ready at SSLLP-GV Store
20230731026 | 2023-07-31 | Forged brass ball valve | Material ready at SSLLP-GV Store
20230731031 | 2023-07-31 | Insulation tapes | Material delivered
20230731038 | 2023-07-31 | Hob and chimney | Material will delivery by next week
20230731044 | 2023-07-31 | Toughned glass | Work under process
20230805041 | 2023-08-05 | Country Grass | Holding for while site not ready
20230807042 | 2023-08-07 | Altec Lappum 7 bags bags | Part material received balance Material delivery by monday
20230807059 | 2023-08-07 | Laptop Bag | No stock at SSLLP NEXT Week will come
20230811012 | 2023-08-11 | Toughned glass | Work under progress
20230811013 | 2023-08-11 | HOB and chimney | Material will delivery by next week
20230811021 | 2023-08-11 | UPVC windows | Work under progress
20230812024 | 2023-08-12 | Anchor bolts | Material will delibery by thursday
20230818027 | 2023-08-18 | MS L angle and MS flat | Material delivered.
20230819021 | 2023-08-19 | Consumbles | Material delivery by monday
20230821025 | 2023-08-21 | SWimming pool Equipment | Site not yet ready
20230821026 | 2023-08-21 | Swimming pool filter plant | Site not yet ready
20230821027 | 2023-08-21 | Swimming pool filter plant | Site not yet ready
20230822035 | 2023-08-22 | Consumbles dust pan | Material delivery by monday
20230823038 | 2023-08-23 | Aluminum louvers | Material delivery by tuesday
20230824046 | 2023-08-24 | Loft tanks | Material available at SSLLP to delivery by monday
20230824026 | 2023-08-24 | Nylone rope | Delivered
20230824046 | 2023-08-24 | Loft tanks | Material available at SSLLP to delivery by monday
20230824053 | 2023-08-24 | Long bend | Material delivery by tuesday
20230825025 | 2023-08-25 | SS name plate | Under process
20230826021 | 2023-08-26 | Cable tray | Material delivery by tuesday
20230826030 | 2023-08-26 | UPVC Windows | Work under progress
20230828039 | 2023-08-28 | Tan brown granite antiskid | Material ready at SSLLP
20230828040 | 2023-08-28 | Electrical wires and conducting pipes | Part material deliverd balance delivery by tuesday
20230828031 | 2023-08-28 | False ceiling Lights | Material delivery by tuesday
20230829033 | 2023-08-29 | Electrical module plates | Part material received balance material delivery by tuesday
20230829032 | 2023-08-29 | Electrical module plates | Part material received balance material delivery by tuesday
20230830062 | 2023-08-30 | LED Lights 20wats | Material delivered by today Evening