## NE
Prepared by: | K Mounika
Report Date | 13.09.2023
Site | SOV-III
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
20230619039 | 19.06.2023 | Panel Door | Next week delivery
20230725010 | 25.07.2023 | Panel Doors | Material recieved
20230802001 | 02.08.2023 | Test apparatus slump cone | Follow up with supplier
20230816018 | 16.08.2023 | wall putty cement | Next week delivery
20230819013 | 19.08.2023 | Stationary | Collect from SSLLP
20230821018 | 21.08.2023 | wash basin waste coupling | Follow up with supplier
20230821018 | 21.08.2023 | wash basin waste coupling | Follow up with supplier
20230904010 | 04.09.2023 | Panel Doors | part recieved balance next week delivery
20230904022 | 04.09.2023 | Deep box,metal box 6way ,8 way | part recieved balance next week delivery
20230904039 | 04.09.2023 | Panel doors and Hardware locks ,hinges | Collect from SSLLP
20230904040 | 04.09.2023 | Panel doors and Hardware locks ,hinges | Collect from SSLLP
20230904045 | 04.09.2023 | Pvc pipe,bends ,clamps,vent cover ,elbow | Collect from SSLLP
20230904059 | 04.09.2023 | CPVC Pipe ,elbow,tee ,coupling,union | Collect from SSLLP
20230904041 | 04.09.2023 | Pvc pipe,bends ,clamps,vent cover ,elbow | Material recieved
20230904043 | 04.09.2023 | Pvc pipe,bends ,clamps,vent cover ,elbow | Material recieved
20230904048 | 04.09.2023 | CPVC Pipe ,elbow,tee ,coupling,union | Material recieved
20230904052 | 04.09.2023 | CPVC Pipe ,elbow,tee ,coupling,union | Material recieved
20230904058 | 04.09.2023 | CPVC Pipe ,elbow,tee ,coupling,union | Material recieved
20230906027 | 06.09.2023 | CPVC ball valve | Material recieved
20230811015 | 11.08.2023 | Tan brown granite | Material recieved