## Vista
Prepared by: | Asha jyothi
Report Date | 23-06-2023 to 06-09-2023
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230908042 | 2023-09-08 | 1,2,3 | Hardware | PO has issued
20230908019 | 2023-09-08 | 1 | Solid blocks | PO has issued
List of requisitions Where PO/WO is prepared and items have not received at site
20230623036 | 2023-06-23 | 2,3 | MS Z-Angle | Material delivered today
20230630050 | 2023-06-30 | 1 | Breath analyser | Online purchae
20230704001 | 2023-07-04 | 1 | Sports | Supplier arranging material
20230720016 | 2023-07-20 | 3 | General item-Carrom board cover | Online purchase
20230818026 | 2023-08-18 | 1 | Consumables | PO Closed,raise new requisition
20230819059 | 2023-08-19 | 13 | Tiles | Received
20230823021 | 2023-08-23 | 1 | Tiles | Collect part material from ssllp
20230831012 | 2023-08-31 | 2 | Hardware | Supplier arranging material
20230904051 | 2023-09-04 | 1,2,3 | Electrical -Metal box | Material delivered today
20230906040 | 2023-09-06 | 1 | MS-L patti | Supplier arranging material