## Vista
Prepared by: | S.Jaysudha
Report Date | 2023-09-15
Site | Dr. NRK
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Delivered
20230809037
20230809041 | 2023-08-09 | SD Card | Cancelled by Sunil Sir
20230828020 | 2023-08-28 | Web Camera | Collect from SSLLP.
20230901009 | 2023-09-01 | Equip: Effulent treatment plant | Under discussion
20230901010 | 2023-09-01 | Equip: Sewage treatment plant | Under discussion
20230513022 | 13.05.23 | Nitobond bonding agent
20230908001 | 2023-09-08 | Pavers Rectangle | Collect from SSLLP@GV
List of requisitions Where PO/WO is prepared and items have not received at site
20230620027 | 2023-06-20 | Fire doors | part delivered partdeliver by saturday
20230908004 | 2023-09-08 | All in one computer | Delivered