## Vista
Prepared by: | Asha jyothi
Report Date | 30-06-2023 to 13-09-2023
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914048 | 2023-09-14 | 1 | I-Pad | MD sir congirmation pending
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230630050 | 2023-06-30 | 1 | Breath analyser | Online purchae
20230720016 | 2023-07-20 | 3 | General item-Carrom board cover | Online purchase
20230823021 | 2023-08-23 | 1 | Tiles | Collect part material from ssllp
20230908019 | 2023-09-08 | 1 | Bricks | will be delivered by today
20230913001 | 2023-09-13 | 3 to 11 | Consumables | will be delivered by this week
20230912023 | 2023-09-12 | 1 | Plumbing | Collect material from supplier
20230913063 | 2023-09-13 | 1,2 | Hardware | Material is ready,Collect material from supplier