## NE
Prepared by: | K Mounika
Report Date | 20.09.2023
Site | Serene Construction LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
20230908021 | 08.09.2023 | Tiles | Next week delivery