## Vista
Prepared by: | Asha jyothi
Report Date | 30-06-2023 to 20-09-2023
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914048 | 2023-09-14 | 1 | I-Pad | MD sir congirmation pending
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230630050 | 2023-06-30 | 1 | Breath analyser | Online purchae
20230720016 | 2023-07-20 | 3 | General item-Carrom board cover | Online purchase
20230823021 | 2023-08-23 | 1 | Tiles | Collect part material from ssllp
20230913062 | 2023-09-13 | 1,2,3,4 | Plumbing-PVC | will be delivered by this week
20230913063 | 2023-09-13 | 1,2 | Hardware | Received
20230920042 | 2023-09-20 | 1 | Plumbing | Received
20230920021 | 2023-09-20 | 1,2 | Hardware | Received
20230913001 | 2023-09-13 | 6 | Consumables | Received
20230920047 | 2023-09-20 | 1 | Granite | Collect material from SSLLP
20230920048 | 2023-09-20 | 1 | SS Sink | Collect part material from ssllp
20230914003 | 2023-09-14 | 1 | Panel doors | Collect material from SSLLP