## NE
Prepared by: | K Mounika
Report Date | 28/09/2023
Site | SOV-III
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
20230821018 | 21.08.2023 | CP Wash basin waste coupling | Material recieved
20230904022 | 04.09.2023 | Electrical 8 way metal box | Material recieved
20230909024 | 09.09.2023 | deep box ,junction box | Collect from SSLLP
20230909027 | 09.09.2023 | wall mixture ,pilla cock ,angle cock | Collect from SSLLP
20230911012 | 11.09.2023 | z angles | Material recieved
20230913061 | 13.09.2023 | pvc single socket pipe | Material recieved
202309130339 | 13.09.2023 | Door closer | Material recieved
20230913066 | 13.09.2023 | CPVC end cap | Collect from SSLLP
20230916047 | 16.09.2023 | metal box 6 way and 8 way | Material recieved
20230916048 | 16.09.2023 | janatha paste | Material recieved
20230921006 | 21.09.2023 | WPC door frame | Follow up with supplier
20230921009 | 21.09.2023 | Conducting pipes | Collect from SSLLP