## Vista
Prepared by: | S.Jaysudha
Report Date | 2023-10-06
Site | Dr. NRK
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Delivered
20230809037
20230809041 | 2023-08-09 | SD Card | Cancelled by Sunil Sir
20230901009 | 2023-09-01 | Equip: Effulent treatment plant | Under discussion
20230901010 | 2023-09-01 | Equip: Sewage treatment plant | Under discussion
20230513022 | 13.05.23 | Nitobond bonding agent
List of requisitions Where PO/WO is prepared and items have not received at site
PO.No. | PO. DATE | Material Descscription | Purchase Officer - Remarks
20230920064 | 2023-09-20 | Hand Gloves | Delivered
20230913086 | 2023-09-13 | Vinyl flooring | Deliver by next week
20230911026 | 2023-09-11 | Copper cable-2.5sqmm-3cor | Deliver by saturday
20230620034 | 2023-06-20 | Fire Doors | Delivered