## Vista
Prepared by: | Asha jyothi
Report Date | 14-08-2023 to 29-09-2023
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914048 | 2023-09-14 | 1 | I-Pad | MD sir congirmation pending
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230823028 | 2023-08-23 | 1 | Tiles | collect material next week
20230914068 | 2023-09-14 | 1,2 | Hardware | Nextweek delivery
20230913002 | 2023-09-13 | 6,11 | Consumables | Collect part material from ssllp
20230920084 | 2023-08-20 | 1 | Granite | collect material next week
20230914067 | 2023-09-14 | 1 | Panel doors | Received
20230923052 | 2023-09-23 | 1,2,3,4 | Door beadings | Next week delivery
20230923054 | 2023-09-23 | 1,2 | Panel doors | Next week delivery
20230923055 | 2023-09-23 | 1,2 | Panel doors | Received
20230923050 | 2023-09-23 | 1,2 | Hardware-Hinges | Next week delivery
20230928040 | 2023-09-28 | 1 | Blue sheet | Received
20230929035 | 2023-09-29 | 1 | Electrical | Collect part material from ssllp