## Vista
Prepared by: | Asha jyothi
Report Date | 14-08-2023 to 07-10-2023
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20231003034 | 2023-10-03 | 1 | I-Pad | MD sir congirmation pending
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230823028 | 2023-08-23 | 1 | Tiles | collect material next week
20230914068 | 2023-09-14 | 1,2 | Hardware | Received
20230913002 | 2023-09-13 | 6,11 | Consumables | Received
20230920084 | 2023-08-20 | 1 | Granite | collect material next week
20230923052 | 2023-09-23 | 1,2,3,4 | Door beadings | Received
20230923050 | 2023-09-23 | 1,2 | Hardware-Hinges | Received
20230929035 | 2023-09-29 | 1 | Electrical | Collect part material from ssllp
20231003007 | 2023-10-03 | 1 | Peripherals | Online purchase
20230930014 | 2023-10-03 | 5 | Plumbing | Received
20231005014 | 2023-10-05 | 1 | Electrical | Received
20231005013 | 2023-10-05 | 1 | Hardware-Bombay nails | Received
20231006032 | 2023-10-07 | 1 | General item -Safety jacket | Received
20231006031 | 2023-10-07 | 1 | Tools-Helmets | Received