## Vista
Prepared by: | S.Jaysudha
Report Date | 2023-10-20
Site | Dr. NRK
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Delivered
20230809037
20230809041 | 2023-08-09 | SD Card | Cancelled by Sunil Sir
20230901009 | 2023-09-01 | Equip: Effulent treatment plant | Under discussion
20230901010 | 2023-09-01 | Equip: Sewage treatment plant | Under discussion
20230513022 | 13.05.23 | Nitobond bonding agent
List of requisitions Where PO/WO is prepared and items have not received at site
Po.No. | Po.date | Item Description | Purchase Officer - Remarks
20231012053 | 2023-10-12 | Country grass | Deliver by next week
20231012052 | 2023-10-12 | Neem Powder & vermicompost | Delivered
20231011012 | 2023-10-11 | Solid blocks | Delivered
20231007028 | 2023-10-07 | Copper lugs & cables | Delivered
20231010020 | 2023-10-10 | Manhole covers | Deliver by next week
20231003009 | 2023-10-03 | CC speed breaker | Delivered
20230929058 | 2023-09-29 | Ms props | Deliver by next week
20231010018 | 2023-10-10 | Tandoor stone | Delivered
20231004004 | 2023-10-01 | carpet grass | Deliver by next week
20230913069 | 2023-09-13 | Vinyle flooring | Delivered