## Vista
Prepared by: | Asha jyothi
Report Date | 2023-11-01
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20231003034 | 2023-10-03 | 1 | I-Pad | Rejected
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230504034 | 2023-04-21 | 1 | Electrical | Under Production Approx delivery date(2.11.2023)
20230428021 | 2023-04-28 | 1 | Electrical | Under Production Approx delivery date(2.11.2023)
20230428022 | 2023-04-28 | 1 | Electrical | Under Production Approx delivery date(2.11.2023)
20230428023 | 2023-04-28 | 1 | Electrical | Under Production Approx delivery date(2.11.2023)
20230428024 | 2023-04-28 | 1 | Electrical | Under Production Approx delivery date(2.11.2023)
20230504030 | 2023-05-04 | 1 | Electrical | Under Production Approx delivery date(2.11.2023)
20230504031 | 2023-05-04 | 1 | Electrical | Under Production Approx delivery date(2.11.2023)
20230505033 | 2023-05-05 | 1 | Electrical | Under Production Approx delivery date(2.11.2023)
20230505028 | 2023-05-05 | 1,2 | Electrical | Under Production Approx delivery date(2.11.2023)
20230505027 | 2023-05-05 | 1 | Electrical | Under Production Approx delivery date(2.11.2023)
20230428027 | 2023-05-05 | 1 | Electrical | Under Production Approx delivery date(2.11.2023)
20230807043 | 2023-08-07 | 1 | Electrical | Under Production Approx delivery date(2.11.2023)
20230920084 | 2023-08-20 | 1 | Granite | This week delivery
20230823028 | 2023-08-23 | 1 | Tiles | collect part material from ssllp
20230929035 | 2023-09-29 | 1 | Electrical | No stock at ssllp
20231003007 | 2023-10-03 | 1 | Peripherals | Online purchase
20231007044 | 2023-10-07 | 3 | Steel | collect material from ssllp
20231017041 | 2023-10-18 | 1 | Hardware-J Bolt | Delivery after payment
20231021031 | 2023-10-24 | 1,2,3,4 | Tiles | collect part material from ssllp
20231021032 | 24.10.2023 | 1 to 8 | Tiles | collect part material from ssllp
20231025034 | 25.10.2023 | 1 to 4 | Plumbing | Next week delivery