## Vista
Prepared by: | B.Sadhana
Report Date | 03.11.2023
Company Name | Modi Realty Pocharam LLP
Site | Nilgiri Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial noof item req | Item Description | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230801018 | 01.08.2023 | 1 | Sofa Set | Online Purchase , Coordinate with Procurement
20230510051 | 10.05.2023 | 1 | Passenger Lift | Work under progress
2023051005 | 10.05.2023 | 1 | Service Lift | Work under progress
List of requisitions Where PO/WO is prepared and items have not received at site
PO.NO | PO Date | Serial noof item req | Item Description
20230913040 | 12.09.2023 | 1 | Safety belts | Collect from supplier
20230925077 | 23.09.23 | 1&2 | U Bolts | Collect from supplier
20230923002 | 24.09.2023 | 1&2 | Tiles | Part material delivered , balance collect from SSLLP
20231009035 | 09.10.2023 | 1 | Agro Shade Net | Collect from supplier
20231011032 | 09.10.2023 | 1 to 11 | CPVC Material | Stock available at SSLLP , Collect from SSLLP
20231013013 | 12.10.2023 | 1 to 3 | Screws | Collect from supplier
20231016068 | 14.10.2023 | 1 | Screws | Collect from supplier
20231016059 | 16.10.2023 | 1 | Screws | Collect from supplier
20231016050 | 16.10.2023 | 1 | Luppam | Material Delivered
20231017024 | 17.10.2023 | 1 | Doors | Part material delivered , balance collect from SSLLP
20231020003 | 19.10.2023 | 1 | Sockets | Collect from supplier
20231021013 | 21.10.2023 | 1 | Laticrete | Material Delivered
20231025031 | 25.10.2023 | 1 | Mindoors | Collect from supplier