## Vista
Prepared by: | S.Jaysudha
Report Date | 2023-11-03
Site | Dr. NRK
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Delivered
20230809037
20230809041 | 2023-08-09 | SD Card | Cancelled by Sunil Sir
20230901009 | 2023-09-01 | Equip: Effulent treatment plant | Under discussion
20230901010 | 2023-09-01 | Equip: Sewage treatment plant | Under discussion
20230513022 | 13.05.23 | Nitobond bonding agent
List of requisitions Where PO/WO is prepared and items have not received at site
Po.No. | Po.date | Item Description | Purchase Officer - Remarks
20230929058 | 2023-10-04 | Ms Prop | Deliver by Saturday
20231010020 | 2023-10-10 | Manhole covers | Delivered
20231004004 | 2023-10-04 | Carpet grass | Delivered