## Vista
Prepared by: | B.Sadhana
Report Date | 10.11.2023
Company Name | Modi realty miryalaguda
Site | A V R Gulmohar Homes
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | serial no | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
PO.NO | Po Date | Serial noof item req | Item Description
20231016052 | 16.10.2023 | 3&4 | Healt Faucet & pillar cock | Material Delivered
20231004022 | 04.10.2023 | 5 | Torch light for Security | Material Delivered
20230803047 | 03.08.2023 | 1 | Lift Equipment | Coordinate with JOHNSON
20231025035 | 25.10.2023 | 1 | 4 Model plate | Material Delivered
20231026029 | 26.10.2023 | 1 | Flush tank | Material Delivered
20231031022 | 31.10.2023 | 1 | DC Card | Material Delivered
20231031021 | 31.10.2023 | 1 | CC Cameras | Collect from SSLLP