## Vista
Prepared by: | B.Sadhana
Report Date | 16.11.2023
Company Name | Modi Realty Pocharam LLP
Site | Nilgiri Heights
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial noof item req | Item Description | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230801018 | 01.08.2023 | 1 | Sofa Set | Online Purchase , Coordinate with Procurement
20230510051 | 10.05.2023 | 1 | Passenger Lift | Work under progress
2023051005 | 10.05.2023 | 1 | Service Lift | Work under progress
List of requisitions Where PO/WO is prepared and items have not received at site
PO.NO | PO Date | Serial noof item req | Item Description
20230923002 | 24.09.2023 | 1 & 2 | Tiles | Part material Delivered , Balance Collect from SSLLP
20231009035 | 09.10.2023 | 1 | Agro Shade Net | Collect from supplier
20231011032 | 09.10.2023 | 1 to 11 | CPVC Material | Collect from ssllp
20231.2503 | 25.10.2023 | 1 | Main doors | Material Delivered
20231031019 | 31.10.2023 | 1 | CC Cameras | Stock available at SSLLP , Collect from ssllp
20231106003 | 06.11.2023 | 1 | Reducer Bush | Collect from Supplier