## Vista
Prepared by: | Asha jyothi
Report Date | 2023-11-21
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230504034 | 2023-04-21 | 1 | Electrical | Under Production
20230428021 | 2023-04-28 | 1 | Electrical | Under Production
20230428022 | 2023-04-28 | 1 | Electrical | Under Production
20230428023 | 2023-04-28 | 1 | Electrical | Under Production
20230428024 | 2023-04-28 | 1 | Electrical | Under Production
20230504030 | 2023-05-04 | 1 | Electrical | Under Production
20230504031 | 2023-05-04 | 1 | Electrical | Under Production
20230505033 | 2023-05-05 | 1 | Electrical | Under Production
20230505028 | 2023-05-05 | 1,2 | Electrical | Under Production
20230505027 | 2023-05-05 | 1 | Electrical | Under Production
20230428027 | 2023-05-05 | 1 | Electrical | Under Production
20230807043 | 2023-08-07 | 1 | Electrical | Under Production
20230920084 | 2023-08-20 | 1 | Granite | collect part material from ssllp
20230823028 | 2023-08-23 | 1 | Tiles | collect part material from ssllp
20231003007 | 2023-10-03 | 1 | Peripherals | Online purchase
20231021031 | 2023-10-24 | 1,2,3,4 | Tiles | collect part material from ssllp
20231028011 | 28.10.2023 | 1 | Granite | collect material from ssllp
20231103025 | 03.11.2023 | 1,2,3,4 | MS-Grills | Under fabrication
20231103023 | 03.11.2023 | 1,2,3,4 | MS-Grills | Under fabrication
20231103026 | 03.11.2023 | 1,2,3,4 | MS-Grills | Under fabrication
20231103012 | 03.11.2023 | 1,2 | Hardware | Material deliverd by this week
20231103011 | 03.11.2023 | 1 | Doors | Delivered by this week
20231107009 | 07.11.2023 | 1 | Plastic chairs | Delivered by this week
20231109012 | 09.11.2023 | 1 | Flush door | Received
20231114017 | 14.11.2023 | 1 | Electrical | Received
20231115017 | 15.11.2023 | 1 | Plumbing | Received
20231118008 | 18.11.2023 | 1,2 | Chemical | Received
20231117001 | 17.11.2023 | 1 to 9 | Electrical | Received
20231117002 | 17.11.2023 | 1 to 12 | Electrical | Received
20231117022 | 17.11.2023 | 1 to 8 | Consumables | Received