## Vista
Prepared by: | Asha jyothi
Report Date | 2023-12-01
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial no of item in req. | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
20230914047 | 2023-09-14 | 1 | Electric bike-OLA | MD sir congirmation pending
List of requisitions Where PO/WO is prepared and items have not received at site
20230504034 | 2023-04-21 | 1 | Electrical | Under Production
20230428021 | 2023-04-28 | 1 | Electrical | Under Production
20230428022 | 2023-04-28 | 1 | Electrical | Under Production
20230428023 | 2023-04-28 | 1 | Electrical | Under Production
20230428024 | 2023-04-28 | 1 | Electrical | Under Production
20230504030 | 2023-05-04 | 1 | Electrical | Under Production
20230504031 | 2023-05-04 | 1 | Electrical | Under Production
20230505033 | 2023-05-05 | 1 | Electrical | Under Production
20230505028 | 2023-05-05 | 1,2 | Electrical | Under Production
20230505027 | 2023-05-05 | 1 | Electrical | Under Production
20230428027 | 2023-05-05 | 1 | Electrical | Under Production
20230807043 | 2023-08-07 | 1 | Electrical | Under Production
20230823028 | 2023-08-23 | 1 | Tiles | Received
20231003007 | 2023-10-03 | 1 | Peripherals | PO closed
20231021031 | 2023-10-24 | 1,2,3,4 | Tiles | collect part material from ssllp
20231103025 | 03.11.2023 | 1,2,3,4 | MS-Grills | Powder coating under process
20231103023 | 03.11.2023 | 1,2,3,4 | MS-Grills | Powder coating under process
20231103026 | 03.11.2023 | 1,2,3,4 | MS-Grills | Powder coating under process
20231103011 | 03.11.2023 | 1 | Doors | Delivered by this week
20231107009 | 07.11.2023 | 1 | Plastic chairs | Received
20231115017 | 15.11.2023 | 1 | Plumbing | collect part material from ssllp
2023117003 | 18.11.2023 | 1 | Plastic covers | Received
20231118029 | 18.11.2023 | 1 | Plastic covers | Received
20231117031 | 17.11.2023 | 1 | MS Railing | Under fabrication
20231117033 | 17.11.2023 | 1 | Haedware | Received
20231117032 | 17.11.2023 | 1 | Haedware | Received
20231123002 | 23.11.2023 | 1 | SS Sink | Received