## Vista
Prepared by: | B.Sadhana
Report Date | 01.12.2023
Company Name | Modi realty miryalaguda
Site | A V R Gulmohar Homes
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | serial no | Material Description | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
PO.NO | Po Date | Serial noof item req | Item Description
20230803047 | 03.08.2023 | 1 | Lift Euipment | Payment Pending
20231031021 | 31.10.2023 | 1 | CC Cameras | Delivery on this week
20231123013 | 24.11.2023 | 1 to 3 | Sanitary Items | Delivery on this week
20231123012 | 24.11.2023 | 1 to 10 | CP Items | Delivery on this week