## Vista
Prepared by: | B.Sadhana
Report Date | 01.12.2023
Company Name | MMRK-LLP
Site | GHT
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Serial noof item req | Item Description | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions Where PO/WO is prepared and items have not received at site
PO No | PO Date | Serial no of item req | Item Description
20231101031 | 2023-11-01 | 1 to 4 | MS Grills | Material ready at SSLLP , Collect from SSLLP
20231114029 | 14.11.2023 | 1 | MS Grills | Work under Progress , Next week Delivery .
20231114030 | 14.11.2023 | 1 | MS Grills | Work under Progress , Next week Delivery .
20231114035 | 14.11.2023 | 1 | MS Grills | Work under Progress , Next week Delivery .